Software Project Management

# Lab 1: Draw the precedence network diagram and Gantt Chart using MS Project.

(Consider the following table of information: )

| Activity | Duration(week) | Precedents |
| --- | --- | --- |
| A | 8 | None |
| B | 6 | None |
| C | 5 | A |
| D | 6 | B |
| E | 5 | B |
| F | 12 | None |
| G | 5 | E,F |
| H | 4 | C,D |

# Lab 2: Draw the precedence network diagram and Gantt Chart using MS Project.

| Activity | Duration | Depends on |
| --- | --- | --- |
| A | 5 days | - |
| B | 1 days | - |
| C | 2 days | A |
| D | 3 days | A |
| E | 2 days | A |
| F | 3 days | C |
| G | 4 days | D |
| H | 2 days | B,E |
| I | 1 days | H |
| J | 1 days | F,G.I |

# Lab 3: Draw the precedence network diagram and Gantt Chart using MS Project.

(Consider the following table of information: )

| Activity | Duration(week) | Precedents |
| --- | --- | --- |
| A | 3 | None |
| B | 5 | None |
| C | 4 | None |
| D | 2 | A |
| E | 3 | B |
| F | 9 | C |
| G | 8 | D,E |
| H | 7 | B |
| I | 7 | F,H |

# Lab 4: Draw the precedence network diagram and Gantt Chart using MS Project.

(Consider the following table of information: )

| Activity | Duration(week) |
| --- | --- |
| Specify overall | 34 |
| Specify module A | 20 |
| Specify module B | 15 |
| Specify module C | 25 |
| Check specification | 2 |
| Design module A | 7 |
| Design module B | 6 |
| Design module C | 4 |
| Code /test A | 30 |
| Code /test B | 28 |
| Code /test C | 15 |
| System Integration | 6 |

# Lab 5: Draw the critical path diagram for the tabulated activities. Identify the critical path and duration of the project.

(Consider the following table of information: )

| Activity | Duration | Immediate Predecessor |
| --- | --- | --- |
| A | 9 | - |
| B | 10 | - |
| C | 9 | A |
| D | 15 | B, C |
| E | 12 | B |
| F | 4 | D |
| G | 8 | E |
| H | 10 | F, G |

# Lab 6: Consider the cash flow of four projects. The cash flow is accounted for at the end of each fiscal year. Calculate ROI and NPV with 10% discount rate for the following data using excel.

(Consider the following table of information: )

| Year | Project 1 | Project 2 | Project 3 | Project 4 |
| --- | --- | --- | --- | --- |
| 0 | -100,000 | -1,000,000 | -100,000 | -120,000 |
| 1 | 10,000 | 200,000 | 30,000 | 30,000 |
| 2 | 10,000 | 200,000 | 30,000 | 30,000 |
| 3 | 10,000 | 200,000 | 30,000 | 30,000 |
| 4 | 20,000 | 200,000 | 30,000 | 30,000 |
| 5 | 100,000 | 300,000 | 30,000 | 75,000 |
| Net Profit | 50,000 | 100,000 | 50,000 | 75,000 |

# Lab 7: Perform Earned value analysis of the given project using excel. Calculate ACWP, BCWP, BCWS, SPI, CPI, SV,CV.

| Activity | Precedeer | Duration (days) | Cost per day | Total cost |
| --- | --- | --- | --- | --- |
| A |  | 2 | 300 | 600 |
| B | A | 3 | 400 | 1200 |
| C | B | 3 | 400 | 1200 |
| D | B | 2 | 200 | 400 |
| E | D | 3 | 100 | 300 |

| Field Report at the end of 7 days |  |  |
| --- | --- | --- |
| Activity | Actual % Complete | Incurred Cost |
| A | 100 | 600 |
| B | 100 | 1400 |
| C | 33 | 500 |
| D | 50 | 200 |
| E | 0 | 0 |